## Sheet1
Proposal project planning
Part | Weeks | Project work
1 | 12/02 - 19/02 - 26/02 - 04/03 | Obtain a simplified model of the crane (point mass, perfect motors etc.)
Design general (open loop) model to control the robot. Model contains two important parts: 1.Determining the (optimal) path to reach the destination with the swinging 2. Converting this path into actuation of the robot. (See pictures attached in mail)
Code basic functions in c
Implement functions and test basic model
2 | 11/03- 18/03- 25/03 | Make model of the crane more realistic. Closed loop control. Include errors of motors/sensors if necessary (only for simulation).
Adapt robot's functions to a real-life problem. P.e. moving crates in storage AB Inbev
Design of improved robot functions
Start design throwable gripper
| 01/04 - 08/04 | Eastern holidays - buffer weeks to finish work on part 1-2 or start work on part 3
3 | 15/04- 22/04- 29/04- 06/05- 13/05- 20/05 | Implementation of improved functions and realistic model
Continue design throwable gripper
Multiple situations adaptation